# PAN Services – 3-Month Operational Roadmap

(Powered by VCSHub)

Objective: Strengthen PAN Services’ brand identity, establish digital presence, and attract qualified leads for architectural/real estate services.

## Month 1: Brand Foundation & Digital Setup

Week 1–2

- Develop Brand Identity Assets:

  - Logo refinements, brand colors, typography.

  - Standardized templates (presentations, proposals, social posts).

- Create/optimize Instagram & LinkedIn Pages:

  - Professional bios, highlights, banners, pinned posts.

- Content Kickoff:

  - “About PAN Services” carousel.

  - 1–2 educational posts (architecture insights / lifestyle tips).

Week 3–4

- Website/Portfolio setup (if not already): landing page + project showcase.

- Post client credibility content:

  - “Our Projects” highlights (visual before/after).

  - 1 video reel (design story or site walkthrough).

- Implement content calendar for next 2 months.

## Month 2: Visibility & Engagement

Week 5–6

- Launch “Did You Know?” content series (architecture facts + PAN projects).

- Publish mini client testimonial video/reel.

- Run organic growth campaign on Instagram/LinkedIn (target: +300 new followers).

Week 7–8

- Host live Q&A session/webinar on “Modern Home Design Trends” (build authority).

- Release case study-style carousel (a completed project breakdown).

- Begin email newsletter pilot (monthly roundup).

## Month 3: Lead Generation & Consolidation

Week 9–10

- Run targeted ad campaign (Instagram/LinkedIn) showcasing services to HNIs & developers.

- Publish client-centric blog/LinkedIn article (thought leadership).

- Design lead magnet (free PDF guide: “5 Essentials Before Starting Your Building Project”).

Week 11–12

- Compile PAN Services Portfolio PDF (high-quality showcase for clients).

- Launch referral incentive program (encourage word-of-mouth).

- Deliver monthly performance report (growth in reach, engagement, and leads).

# End of 3 Months – Key Deliverables

✅ Complete Brand Identity Kit
 ✅ Active Instagram & LinkedIn pages with consistent content
 ✅ 2 Video reels + 6–8 carousels + educational series
 ✅ 1 Live Webinar + 1 Lead Magnet
 ✅ Portfolio Casebook (PDF + Social versions)
 ✅ Growth: +800 organic followers, 10+ leads generated
 ✅ Monthly Reports (showing content performance + engagement insights)

This positions PAN Services not just as another architecture firm, but as a modern, trusted, and client-centric brand with a professional identity and consistent visibility.

Would you like me to now package this into a branded PDF presentation (PAN Services Operational Roadmap) that you can send directly to the client, instead of just text?