# 3-Month Operational Roadmap

Duration: Month 1 → Month 3
Method: Bi-weekly execution cycles (2-week sprints)
Focus: Client Acquisition + Brand Visibility + Internal Systems

## Month 1: Foundation & Visibility

Week 1–2

- CEO:

  - Finish LLC Registration & Pricing Framework.

  - Create draft VCS Report template (metrics: clients, revenue, engagement).

  - Begin outreach pipeline (minimum 15 prospects identified).

- CMO:

  - Set up Instagram professionally (bio, highlights, pinned posts).

  - Design brand kit draft (colors, fonts, templates).

  - Post “We’re Back” + About Us + First Carousel.

Week 3–4

- CEO:

  - Conduct first 3 prospect meetings (document outcomes).

  - Finalize proposal template for client offers.

- CMO:

  - Publish Content Calendar (3 months).

  - Create & release 2 video edits + 2 carousel series.

  - First KSS session draft outline.

## Month 2: Growth & Authority

Week 5–6

- CEO:

  - Refine pricing + service tiers (basic, premium, retainer).

  - Expand outreach to minimum 20 new prospects.

  - Build partnership pipeline (target: 2 potential collabs).

- CMO:

  - Post client showcase content (from pilot project).

  - Host third KSS session.

  - Complete brand consistency manual.

Week 7–8

- CEO:

  - Close 1 new paying client (outside pilot).

  - Finalize mini-pitch deck for partners/investors.

- CMO:

  - Execute Instagram growth push (target: +200 organic followers).

  - Publish branding research piece (global vs local).

  - Release monthly feedback survey to existing clients.

## Month 3: Consolidation & Expansion

Week 9–10

- CEO:

  - Launch sales playbook v1 (document repeatable outreach steps).

  - Secure at least 1 SME/Architect partner discussion.

- CMO:

  - Execute 2nd KSS session.

  - Run mini-campaign for Velo Luxury as a brand extension case study.

  - Batch content for next month (to reduce ad hoc work).

Week 11–12

- CEO:

  - Evaluate performance with first full VCS Report (revenue, leads, content performance).

  - Draft employee hiring framework (roles, cost breakdown).

- CMO:

  - Finalize portfolio casebook (VCSHub’s projects, before/after designs).

  - Grow Instagram to 800+ engaged followers.

  - Create branding expo pitch deck draft (for external authority positioning).

# KPIs

✅ LLC + Pricing Framework
 ✅ VCS Report (tracking system live)
 ✅ 3+ clients onboarded
 ✅ 3 KSS sessions delivered
 ✅ Instagram ~1000 engaged followers
 ✅ Brand kit + manual
 ✅ Proposal + Pitch decks ready
 ✅ Hiring framework for first employee(s)